## ProjectProfile
Asset Management System (AMS)
Project ID | AMS
Project Name | Asset Management System (AMS)
Project Description | Inhouse project to manage all the assets.
Version Number | 1
About Document
Prepared by | Role | Date of Preparation
Nikhil Palde | Tester (Manual) | 2023-03-03
Modified by | Role | Date of Review
Akash Dhole | Tester (Automation) | April
Reviewed by | Role | Date of Approval
Anshul Nayak | Associate Manager
Approved by | Role
Smita Kulkarni | Manager

## RTM
Requirement Tracebility Matrix
URL |  | http://10.176.41.10:8080/UatAms/#/login
Req No. | Module ID | Module/Suite Name | Test Cases Count
|  |  | Manual Testcases (Valid) | Automation Testcases(Applicable)
1 | AMS_MD_1 | Login Page Assertion & Functionality | 10 | 4
2 | AMS_MD_2 | Forgot Password Functionality | 7 | 2
3 | AMS_MD_3 | Dashboard Page Assertion & Functionality | 3 | 3
4 | AMS_MD_4 | Assets Module Functionality | 18 | 6
5 | AMS_MD_5 | Employee Module Functionality | 14 | 5
6 | AMS_MD_6 | Request Module Functionality | 0 | 0
7 | AMS_MD_7 | Assets Group Module Functionality | 8 | 2
8 | AMS_MD_8 | Assets Department Module Functionality | 0 | 0
9 | AMS_MD_9 | Assets Vendor Module Functionality | 0 | 0
10 | AMS_MD_10 | Assets Status Module Functionality | 20 | 4
11 | AMS_MD_11 | User Module Functionality | 24 | 5
|  |  | Total Count : 104 | Total Count : 31
Manual Test Cases Count
|  |  | Valid | Invalid
|  |  | 104 | 23
Total
127
Automation Suites
|  |  | Applicable | Not Applicable
|  |  | 8 | 3
Total
11
Automation Test Cases Count
|  |  | Applicable | Not Applicable
|  |  | 31 | 20
Total
51

## Login_page
Module_ID | Automation_Test_Suites | Automation_Test_Cases | Automation Progress | Automation test Status | Automated By | Reamrk | Test case S/N | Test case ID | Test Case DeMDription | Pre-condition | Test Data | Test Steps | Expected Results | Actual Results | Written By | Written On | Last Update Date | Review Comments | Tested By | Reviewed by | Status | Date Tested
Validate and verify the elements of Login Page
AMS_MD_1 | LoginTest | LoginPageAssertionTest | Completed | Pass | Akash | NA | AMS_01 | AMS_TC_01 | Validate that, UI components/Design of Login Page | 1. User should be on AMS Application Login Page |  | 1. Navigate to AMS Application 2. Validate that, "Role" Dropdown should be present 3. Verify "Username and Password" Labels should be Present 3. Verify "Username and Password" Textbox should be Present 4. Verify Visibility Eye Icon should be present for Password 5. Verify "Login" button should be present 6. Verify "Forget Password ?" link should be present | 1. "Role" Dropdown should be present 2. "Username and Password" Labels should be Present 3. "Username and Password" Textbox should be Present 4. Visibility Eye Icon should be present for Password 5. "Login" button should be present 6. "Forget Password ?" link should be present |  | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Pass
|  | NA | Not Present | Not Present |  |  | AMS_02 | AMS_TC_02 | Verify that,Dropdown values for "Role" field | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Click on Dropdown arrow for Role field and verify the values displayed | 1. User should be able to view below options: Admin User | "Select Role" should not be included in List Items of Role 1. User should be able to view below options: Select Role Admin User | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Fail
|  | NA | Not Present | Not Present |  |  | AMS_03 | AMS_TC_03 | Verify that, if user can select value from Role dropdown | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Click on Dropdown arrow for Role field 3. Select Admin/User option | User should be able to select value from Role Dropdown |  | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Pass
|  | LoginValidCredTest | Completed | Pass | Akash | NA | AMS_04 | AMS_TC_04 | Verify that, Username Textbox is editable or not | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Verify that, Username Textbox is editable | User should be able to enter the Username |  | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Pass
|  |  | Completed | Pass | Akash | NA | AMS_05 | AMS_TC_05 | Verify that, Password Textbox is editable or not | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Verify that, Password Textbox is editable | User should be able to enter the Password |  | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Pass
|  |  | Completed | Fail | Akash | Element is not automatable | AMS_06 | AMS_TC_06 | Verify that, Visibility Eye Icon is clickable and password field is either visible as asterisk or bullet signs. | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Verify that, Eye Icon is Clickable | User should be able to view the password and the data AMS password field is either visible as asterisk or bullet signs. | Two separate visiblity eye icon are present to hide/show the password | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Fail
|  |  | Completed | Pass | Akash | NA | AMS_07 | AMS_TC_07 | Verify that, "Login" button is clickable or not | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Verify Login button is clickable | User should be able to click on Log in and navigate to Dashboard |  | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Pass
AMS_MD_2 | ForgotPasswordTest | ForgotPasswordSendOTPButtonTest | Completed | Pass | Akash | NA | AMS_08 | AMS_TC_08 | Verify that, "Forget Password ?" link is clickable | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Verify "Forget Password ?" Link | User should navigated to ResetPassword Page |  | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Pass
|  |  | Completed | Fail | Akash | NA | AMS_09 | AMS_TC_09 | Validate that "Forget Password ?" should be in standarized font | 1. User should be on AMS Application |  | 1. Navigate to AMS Application | "Forget Password ?" Link should be in standardized font | "Forget Password ?" Link is not in standardized font | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Fail
Verify the functionality of Log in Page
AMS_MD_1 | LoginTest | LoginValidCredTest | Completed | Pass | Akash | NA | AMS_09 | AMS_TC_09 | Verify if a user will be able to Log in with a valid username and valid password. | 1. User should be on AMS Application | Username: PiyushChoraria Password: NCS@123 | 1. Navigate to AMS Application | User should be able to login Successfully and navigate to user dashboard |  | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Pass
|  | LoginInValidCredTest | Completed | Pass | Akash | NA | AMS_10 | AMS_TC_10 | Verify if a user will be able to Log in with In-Valid username and valid password. | 1. User should be on AMS Application |  | 1. Navigate to AMS Application | User should be able to vew "You Cannot Logged In, Something went wrong!" message |  | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Pass
|  |  | Completed | Pass | Akash | NA | AMS_11 | AMS_TC_11 | Verify if a user will be able to Log in with a valid username and In-Valid password. | 1. User should be on AMS Application |  | 1. Navigate to AMS Application | User should be able to vew "You Cannot Logged In, Something went wrong!" message |  | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Pass
|  |  | Completed | Pass | Akash | NA | AMS_12 | AMS_TC_12 | Verify if a user will be able to Log in with a In-Valid username and In-Valid password. | 1. User should be on AMS Application |  | 1. Navigate to AMS Application | User should be able to vew "You Cannot Logged In, Something went wrong!" message |  | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Pass
|  | LoginBlankCredTest | Completed | Pass | Akash | NA | AMS_13 | AMS_TC_13 | Verify if a user will be able to Log in with blank username and password. | 1. User should be on AMS Application |  | 1. Navigate to AMS Application | Error Message should be displayed | Error Message is displayed | Akash Dhole | 2023-05-04
Validate the UI compoments of Reset Password Page
AMS_MD_2 | ForgotPasswordTest | ForgotPasswordSendOTPButtonTest | Completed | Pass | Akash | NA | AMS_14 | AMS_TC_14 | Validate that, UI components/Design of ResetPassword Page | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Click on "Forget Password ?" Link 3. Validate "Ncs Logo" should be present 4. Verify "Confirm User Form"Header Message should be present 5. Verify "Role" Dropdown should be present 5. Verify "Enter UserId" Label and Textbox should present 6. Verify "Send OTP" button should be present 7. Verify "Cancel" button should be present | 1. "Ncs Logo" should be present 2. "Confirm User Form"Header Message should be present 3."Role" Dropdown should be present 4."Enter UserId" Label and Textbox should present 5. "Send OTP" button should be present 6. "Cancel" button should be present |  | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Pass
|  | NA | Not Present | Not Present | Akash | NA | AMS_15 | AMS_TC_15 | Verify that,Dropdown values for "Role" field | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Click on "Forget Password?" link 3. Click on Dropdown arrow for Role field and verify the values displayed | 1. User should be able to view below options: Admin User | "Select Role" should not be included in List Items of Role 1. User should be able to view below options: Select Role Admin User | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Fail
|  | NA | Not Present | Not Present | Akash | NA | AMS_16 | AMS_TC_16 | Verify that, if user can select value from Role dropdown | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Click on "Forget Password?" link 3. Click on Dropdown arrow for Role field 4. Select Admin/User option | User should be able to select value from Role Dropdown |  | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Pass
|  | ForgotPasswordSendOTPButtonTest | Completed | Pass | Akash | NA | AMS_17 | AMS_TC_17 | Verify that, UserId Textbox is editable or not | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Click on "Forget Password?" link 3. Click on UserId Textbox is editable | User should be able to enter the Username |  | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Pass
|  |  | Completed | Fail | Akash | Not Confirm about OTP received by registered user or not | AMS_18 | AMS_TC_18 | Verify that, "Send OTP" is Clickable or not | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Click on "Forget Password?" link 3. Click on "Send OTP" button | User should be able to send mail on registered mail ID with OTP |  | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Pass
|  |  | Completed | Pass | Akash | NA | AMS_19 | AMS_TC_19 | Verify that, "Resend OTP" Link is Clickable | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Click on "Forget Password?" link 3. Click on "Send OTP" button | User should be able to resend the OTP | Resend OTP button is not working and has refernce of Reset Password page | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Fail
|  | ForgotPasswordBackButtonTest | Completed | Pass | Akash | NA | AMS_20 | AMS_TC_20 | Verify that, "Cancel" is Clickable or not | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Click on "Forget Password?" link 3. Click on "Cancel" button | User should be navigated back to LoginPage |  | Nikhil Palde | 2023-01-22 |  |  | Aradhana Shinde |  | Pass

## Dashboard
Module_ID | Automation_Test_Suites | Automation_Test_Cases | Automation Progress | Automation test Status | Automated By | Remark | Test case S/N | Test case ID | Test Case DeMDription | Pre-condition | Test Data | Test Steps | Expected Results | Actual Results | Written By | Written On | Last Update Date | Review Comments | Tested By | Reviewed by | Status | Date Tested
Validate the Dashboard Elements
AMS_MD_3 | DashboardModuleTest | DashboardMainPageTest | Completed | Pass | Akash Dhole | Elements that are not automatable: 1. NCS Logo Elements that are not present: 1. "Audit" Option 2. "User Guide: A Simple User Guide for User Use." element not present 3. Recent Asset Transfer Request | AMS_20 | AMS_TC_20 | Validate that, UI components/Design of Dashboard | 1. User should be Login to AMS Application |  | 1. Navigate to AMS Application 2. Login to the Application 3. Validate "NCS Logo" should be present 4. Verify "Dashboard, Master, Utility, Audit" Options 5. Verify "Admin Guide : A Simple Guide for Admin Use" Label should be present with its pdf. 6. Verify "User Guide : A Simple User Guide for User Use." Label should be present with its pdf. 7. Verify "Recent Asset Transfer Request" table 8. Verify "Asset No, Status, Transfer Date, Employee Name, Remark, Created By, Created Date, Items per page, Navigation button" Table Coloumns should be present 9. Verify "Profile Icon" dropdown should be present 10. Verify "UserName, Change Password, Logout" should be present | 1. "NCS Logo" should be present 2. "Dashboard, Master, Utility, Audit" Options 3. "Admin Guide : A Simple Guide for Admin Use" Label should be present with its pdf. 4. "User Guide : A Simple User Guide for User Use." Label should be present with its pdf. 5. "Recent Asset Transfer Request" table 6. "Asset No, Status, Transfer Date, Employee Name, Remark, Created By, Created Date, Items per page, Navigation button" Table Coloumns should be present 7. "Profile Icon" dropdown should be present 8. "UserName, Change Password, Logout" should be present | 7. "Profile Icon" dropdown should be present inside Dashboard frame goin outside the frame and vertical slider is provided | Nikhil Palde | 2023-01-30 |  |  | Aradhana Shinde |  | Fail
Validate the Master Elements
AMS_MD_3 | DashboardModuleTest | MasterModuleTest | Completed | Pass | Akash Dhole | Elements that are not automatable: Elements that are not present: 1. Asset Transfer | AMS_21 | AMS_TC_23 | Verify that, "Master" listItem is clickable or not | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Verify that "Asset, Employee, Asset Transfer, Asset Group, Asset Department, Asset Vendor, Asset Status, Users" ListItem should be Visible | User should view all the opertaions of Utility which should be "Asset, Employee, Asset Transfer, Asset Group, Asset Department, Asset Vendor, Asset Status, Users" |  | Nikhil Palde | 2023-01-01 |  |  | Aradhana Shinde |  | Pass
Validate the Utility Elements
AMS_MD_3 | DashboardModuleTest | UtilityModuleTest | Completed | Pass | Akash Dhole | NA | AMS_22 | AMS_TC_22 | Verify that, "Utility" listItem is clickable or not | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Utility 4. Verify that "Bulk Asset Import, Bulk Employee Import, Utility Tracker" ListItem should be Visible | User should view all the opertaions of Utility which should be "Bulk Asset Import, Bulk Employee Import, Utility Tracker" | All Elements present | Nikhil Palde | 2023-01-01 |  |  | Aradhana Shinde |  | Pass
Validate the Audit Elements
NA | NA | NA | Not Present | Not Present | NA | The item is not present | AMS_23 | AMS_TC_23 | Verify that, "Audit" listItem is clickable or not | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Audit 4. Verify that "Asset Audit, Asset Transfer Audit, Employee Audit, Asset Group Audit, Asset Department Audit, Asset Vendor Audit, Asset Status Audit, Users Audit, Login Tracker" ListItem should be Visible | User should view all the opertaions of Audit which should be "Asset Audit, Asset Transfer Audit, Employee Audit, Asset Group Audit, Asset Department Audit, Asset Vendor Audit, Asset Status Audit, Users Audit, Login Tracker" |  | Nikhil Palde | 2023-01-01 |  |  | Aradhana Shinde |  | Pass

## Master
Module_ID | Automation_Test_Suites | Automation_Test_Cases | Automation Progress | Automation test Status | Automated By | Reamrk | Test case S/N | Test case ID | Test Case Description | Pre-condition | Test Data | Test Steps | Expected Results | Actual Results | Written By | Written On | Last Update Date | Review Comments | Tested By | Reviewed by | Status | Date Tested
Validate the Asset Page Elements
AMS_MD_4 | AssetModuleTest | SearchAssetTest | Completed | Pass | Akash Dhole | NA | AMS_24 | AMS_TC_24 | Verify that, Asset is clickable or not | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset | User should be able to click on "Asset"link. |  | Nikhil Palde | 2023-02-01 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | Elements that are not automatable: 1. NCS Logo Elements that are not present: 1. "List of Assets" header message 2. Search Dropdown 1 3. Search Dropdown 2 4. Search Button 5. "Sort" dropdown" 6. "Sort" button 7. "Export Asset" button | AMS_25 | AMS_TC_25 | Validate that, UI components/Design of Assets page | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Validate "NCS Logo" should be present 6. Verify "Dashboard, Master, Utility, Audit" Options should be present 7. Verify "List of Assets" Header message should be present 8. Verify "Search Textbox, Search dropdown 1, Search Dropdown 2, Search Button" should be present 9. Verify "Sort Dropdown and Sort Button" should be present 10. Verify "Create New Asset" button should be present 11. Verify "Export Asset" button should be present 12. Verify "Asset Table" should be Present 13. Verify "Items per page" Dropdown should be present | 1. "NCS Logo" should be present 2. "Dashboard, Master, Utility, Audit" Options should be present 3. "List of Assets" Header message should be present 4. "Search Textbox" should be present 5. "Items per page" Dropdown should be present 6. "Create New Asset" button should be present 7. "Export Asset" button should be present 8. "Asset Table" should be Present |  | Nikhil Palde | 2023-02-01 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_26 | AMS_TC_26 | Verify that, Search textbox is editable or not | 1. User should be Login to AMS Application 2. User should be on Assets page | Enter : Nikhil | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Serch textbox | User should be able to enter the data and get the records for the same |  | Nikhil Palde | 2023-02-06 |  |  | Nikhil Palde |  | Pass
|  |  | Not Present | Not Present | Akash Dhole | NA | AMS_27 | AMS_TC_27 | Verify that, Search Dropdown 1 is clickable or not | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Serch Dropdown 1 | User should be able to select the Categories from the dropdown |  | Nikhil Palde | 2023-02-06 |  |  | Nikhil Palde |  | Pass
|  |  | Not Present | Not Present | Akash Dhole | NA | AMS_28 | AMS_TC_28 | Verify that, Search Dropdown 2 is clickable or not | 1. User should be Login to AMS Application 2. User should be on Assets page 3. Content from Search Dropdown 1 must be Selected |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Serch Dropdown 1 6. Click on Serch Dropdown 2 | User should be able to select the Categories from the dropdown |  | Nikhil Palde | 2023-02-06 |  |  | Nikhil Palde |  | Pass
|  |  | Not Present | Not Present | Akash Dhole | NA | AMS_29 | AMS_TC_29 | Verify that, Search Button is Clickable | 1. User should be Login to AMS Application 2. User should be on Assets page 3. Content from Search Dropdown 1 and 2 must be Selected |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Serch Dropdown 1 6. Click on Serch Dropdown 2 7. Click on Search Button | User should be able to Click on Search Button and Display the Filtered Data |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
|  |  | Not Present | Not Present | Akash Dhole | NA | AMS_30 | AMS_TC_30 | Verify that, Sort Dropdown is clickable or not | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Sort Dropdown | User should be able to select the Categories from the dropdown |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
|  |  | Not Present | Not Present | Akash Dhole | NA | AMS_31 | AMS_TC_31 | Verify that, Sort Button is clickable or not | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Sort Dropdown 6. Click on Sort Button | User should be able to View all the Records in Sorted format selected |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
|  | GetAllRowsPresent UpdateAssetTest DeleteAssetTest | In Progress | Pass | Akash Dhole | Elements that are not automatable/not in scope: 1. Transfer, 2. Discard, 3. Clone, 4. QR Code Elements that are not present: 1. Category of Asset 2. Reason | AMS_32 | AMS_TC_32 | Validate that, UI components/Design of Asset Table | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Verify "Asset No, Serial Number, Asset Group, Employee Name, Category of Asset, Asset Description, Vendor Name, Capitilization Date, Department, Fixed/Movable, Vendor Code, Employee code, Status, Reason, Audited, Action" Column Header should be present of Asset Table 6. Verify "Edit, Transfer, Discard, Clone, QR Code, Delete, Take Back" Button should be present in Action Coloumn | 1. "Asset No, Serial Number, Asset Group, Employee Name, Category of Asset, Asset Description, Vendor Name, Capitalization Date, Department, Fixed/Movable, Vendor Code, Employee code, Status, Reason, Audited, Action" Column Header should be present of Asset Table 2."Edit, Transfer, Discard, Clone, QR Code, Delete, Take Back" Button should be present in the Action Column |  | Nikhil Palde | 2023-02-01 |  |  | Nikhil Palde |  | Pass
|  | SearchAssetTest | Completed | Pass | Akash Dhole | NA | AMS_33 | AMS_TC_33 | Verify the "Items per page"dropdown has 4 values | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Verify "Items per page" Dropdown | The user should be able to view the following 4 list items in the "Items per page" dropdown list 1. 5 2. 10 3. 15 4. 25
|  | CreateAssetTest | Completed | Pass | Akash Dhole | NA | AMS_34 | AMS_TC_34 | Verify that, Create Asset button is Clickable or not | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Create Asset | User should be able to Navigate to Create Asset form |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
Validate the Add Asset Page Elements
AMS_MD_4 | AssetModuleTest | CreateAssetTest | Completed | Pass | Akash Dhole | NA | AMS_35 | AMS_TC_35 | Validate the UI Components of "Create Assets" form | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. log in to the Application 3. Click on Master 4. Click on Asset 5. Click on Create New Asset 6. Verify Asset No, Asset Category, Asset Serial No, Asset Description, Count, and Remark label with its textbox and Asset Group, Vendor, Status, Asset Type, Department, label and its dropdown should be present 7. Verify Submit and Cancel Button should be present | 1. "Asset No, Asset Category, Asset Serial No, Asset Description, Count, Remark" label with its textbox and "Asset Group, Vendor, Status, Asset Type, Department" label and its dropdown should be present 2. Submit and Cancel Button should be present |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_36 | AMS_TC_36 | Verify that, Asset No Textbox is clickable or not | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Create New Asset 6. Click on Asset No Textbox | User should be able to enter the Asset Number |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
|  |  | Not Present | Not Present | Akash Dhole | NA | AMS_37 | AMS_TC_37 | Verify that, Asset Category Textbox is clickable or not | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Create New Asset 6. Click on Asset Category Textbox | User should be able to enter the Asset Category and should have minimium 2 letters |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_38 | AMS_TC_38 | Verify that, Asset Group dropdown values are selectable | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Create New Asset 6. Click on Asset Group Dropdown | User should be able to select the asset from Asset Group dropdown |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_39 | AMS_TC_39 | Verify that, Vendor dropdown values are selectable | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Create New Asset 6. Click on Vendor Dropdown | User should be able to select the vendor from vendor dropdown |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_40 | AMS_TC_40 | Verify that, Status dropdown values are selectable | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Create New Asset 6. Click on Status Dropdown | User should be able to select the status from Status dropdown |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_40 | AMS_TC_40 | Verify that, Asset Type dropdown values are selectable | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Create New Asset 6. Click on Asset Type Dropdown | User should be able to select the type of Assets from Asset Type dropdown |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_41 | AMS_TC_41 | Verify that, Asset Description textbox is clickable or not | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Create New Asset 6. Click on Asset Description Textbox | User should be able to enter the Asset Description and should have minimium 5 letters |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_42 | AMS_TC_42 | Verify that, Department dropdown values are selectable | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Create New Asset 6. Click on Department Dropdown | User should be able to select the department type from Department dropdown |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
|  |  | Not Present | Not Present | Akash Dhole | NA | AMS_43 | AMS_TC_43 | Verify that, Audit dropdown values are selectable | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Create New Asset 6. Click on Audit Dropdown | User should be able to select the Yes/No for Audit |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_44 | AMS_TC_44 | Verify that, Count textbox is clickable or not | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Create New Asset 6. Click on Count Textbox | User should be able to enter the Count and should have maximum 12 letters |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_45 | AMS_TC_45 | Verify that, Remark textbox is clickable or not | 1. User should be Login to AMS Application 2. User should be on Assets page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Create New Asset 6. Click on Remark Textbox | User should be able to enter the Remark and should have minimium 2 and maximium 100 letters |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_46 | AMS_TC_46 | Verify that, "Submit" is clickable or not | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Create New Asset 6. Click on "Submit" button | User should be to create new asset |  | Nikhil Palde | 2023-02-07 |  |  | Aradhana Shinde |  | Pass
|  | ClickCancelBtnOnCreateAsset | Completed | Pass | Akash Dhole | NA | AMS_47 | AMS_TC_47 | Verify that, "Cancel" is clickable or not | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Create New Asset 6. Click on "Cancel" button | User should be navigated back to Asset Page |  | Nikhil Palde | 2023-02-07 |  |  | Aradhana Shinde |  | Pass
Validate the Employee Page Elements
AMS_MD_5 | EmployeeModuleTest | SerachEmployeeTest | Completed | Pass | Akash Dhole | NA | AMS_48 | AMS_TC_48 | Verify that, Employee is clickable or not | 1. User should be Login to AMS Application 2. User should be on Employee page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Employee | User should be able to click on "Employee" link. |  | Nikhil Palde | 2023-02-13 |  |  | Nikhil Palde |  | Pass
|  | GetAllRowsPresent CreateEmployeeTest SerachEmployeeTest | Completed | Pass | Akash Dhole | Elements that are not automatable: 1. NCS Logo Elements that are not present: 1. "List of Employees" header message 2. Search Dropdown 3. Search Button | AMS_49 | AMS_TC_49 | Validate that, UI components/Design of Employee page | 1. User should be Login to AMS Application 2. User should be on Employee page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Employee 5. Validate "NCS Logo" should be present 6. Verify "Dashboard, Master, Utility, Audit" Options should be present 7. Verify "List of Employees" Header message should be present 8. Verify "Search Texbox, Search dropdown, Search Button" should be present 9. Verify "Create Employee" button should be present 10 Verify "Employee Table" should be Present 11. Verify "Items per page" Dropdown should be present | 1. "NCS Logo" should be present 2. "Dashboard, Master, Utility, Audit" Options should be present 3. "List of Employee" Header message should be present 4. "Search Texbox, Search dropdown, Search Button" should be present 5. "Create Employee" button should be present 6. "Employee Table" should be Present 7. "Items per page" Dropdown should be present |  | Nikhil Palde | 2023-02-13 |  |  | Nikhil Palde |  | Pass
|  | SearchEmployeeTest | Completed | Pass | Akash Dhole |  | AMS_50 | AMS_TC_50 | Verify that, Search textbox is editable or not | 1. User should be Login to AMS Application 2. User should be on Employee page | Enter : Nikhil | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Employee 5. Click on Serch textbox | User should be able to enter the data and get the records for the same |  | Nikhil Palde | 2023-02-06 |  |  | Nikhil Palde |  | Pass
|  | NA | Not Present | Not Present | Akash Dhole | NA | AMS_51 | AMS_TC_51 | Verify that, Search Dropdown is clickable or not | 1. User should be Login to AMS Application 2. User should be on Employee page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Employee 5. Click on Serch Dropdown | User should be able to select the Categories from the dropdown |  | Nikhil Palde | 2023-02-06 |  |  | Nikhil Palde |  | Pass
|  | NA | Not Present | Not Present | Akash Dhole | NA | AMS_52 | AMS_TC_52 | Verify that, Search Button is Clickable | 1. User should be Login to AMS Application 2. User should be on Employee page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Employee 5. Select from Search Dropdown 6. Click on Serch Button | User should be able to Click on Search Button and Display the Filtered Data |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
|  | GetAllRowsPresent UpdateEmployeeTest DeleteEmployeeTest | In Progress | Pass | Akash Dhole | NA | AMS_53 | AMS_TC_53 | Validate that, UI components/Design of Employee Table | 1. User should be Login to AMS Application 2. User should be on Employee page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Employee 5. Verify "Employee Id, Employee Code, Employee Name, Employee Status, Employee Date of Joining, Employee Email Id, Action"Column Header should be present of Asset Table 6.Verify "Edit, Delete" Button should be present in Action Coloumn | 1. "Employee Id, Employee Code, Employee Name, Employee Status, Employee Date of Joining, Employee Email Id, Action" Column Header should be present of Asset Table 2."Edit, Delete" Button should be present in Action Coloumn |  | Nikhil Palde | 2023-02-01 |  |  | Nikhil Palde |  | Pass
|  | SearchEmployeeTest | Completed | Pass | Akash Dhole | NA | AMS_54 | AMS_TC_54 | Verify the "Items per page"dropdown has 4 values | 1. User should be Login to AMS Application 2. User should be on Employee page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Employee 5. Verify "Items per page" Dropdown | User should be able to view following 4 list items in the "Items per page"dropdown list 1. 5 2. 10 3. 15 4. 25 |  | Nikhil Palde | 2023-02-07
|  | CreateEmployeeTest | Completed | Pass | Akash Dhole | NA | AMS_55 | AMS_TC_55 | Verify that, Create Employee button is Clickable or not | 1. User should be Login to AMS Application 2. User should be on Employee page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Employee 5. Click on Create Employee | User should be able to Navigate to Create Employee form |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
Validate Create Employee Page Elements
AMS_MD_5 | EmployeeModuleTest | CreateEmployeeTest | Completed | Pass | Akash Dhole | NA | AMS_56 | AMS_TC_56 | Validate the UI Components of Create Employee page | 1. User should be Login to AMS Application 2. User should be on Create Employee page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Employee 5. Click on Create New Emploeyee 6. Verify "Employee Code, Employee Name, Employee Email ID" Label and with Its textbox should be present 7. Verify Employee Satatus Dropdown should be present 8. Verify "Employee Date of Joining" calendar dhould be present 9. Verify Submit and Cancel Button should be present | 1."Employee Code, Employee Name, Employee Email ID" Label and with Its textbox should be present 2. "Employee Status" Dropdown should be present 3. "Employee Date of Joining" calendar dhould be present 4. Submit and Cancel Button should be present |  | Nikhil Palde | 2023-02-08 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_57 | AMS_TC_57 | Verify that, Employee Code textbox is editable or not | 1. User should be Login to AMS Application 2. User should be on Add Employee page | Enter : 12345 | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Employee 5. Click on Create New Employee 6. Click on Employee Code textbox | User should be able to enter the Employee Code |  | Nikhil Palde | 2023-02-08 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_58 | AMS_TC_58 | Verify that, Employee Name is editable or not | 1. User should be Login to AMS Application 2. User should be on Add Employee page | Enter : Nikhil | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Employee 5. Click on Create New Employee 6. Click on Employee Name textbox | User should be able to enter the Employee Name |  | Nikhil Palde | 2023-02-08 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_59 | AMS_TC_59 | Verify that, Employee Status Dropdown is selectable or not | 1. User should be Login to AMS Application 2. User should be on Add Employee page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Employee 5. Click on Create New Employee 6. Click on Employee Status Dropdown | User should be able to select the Categories from the Employee Status Dropdown |  | Nikhil Palde | 2023-02-08 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_60 | AMS_TC_60 | Verify that, "Employee Date of Joining" Date is selectable or not | 1. User should be Login to AMS Application 2. User should be on Add Employee page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Employee 5. Click on Create New Employee 6. Click on Employee Status Dropdown | User should be able to select the Categories from the Employee Status Dropdown |  | Nikhil Palde | 2023-02-08 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_61 | AMS_TC_61 | Verify that, Employee Email ID textbox is editable or not | 1. User should be Login to AMS Application 2. User should be on Add Employee page | Email : np@gamil.com | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Employee 5. Click on Create New Employee 6. Click on Employee Code textbox | User should be able to enter the Employee Email ID |  | Nikhil Palde | 2023-02-08 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_62 | AMS_TC_62 | Verify that, "Submit" is clickable or not | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Employee 5. Click on Create New Employee 6. Click on "Submit" button | User should be to create new asset |  | Nikhil Palde | 2023-02-08 |  |  | Aradhana Shinde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_63 | AMS_TC_63 | Verify that, "Cancel" is clickable or not | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset 5. Click on Create New Employee 6. Click on "Cancel" button | User should be navigated back to Asset Page |  | Nikhil Palde | 2023-02-08 |  |  | Aradhana Shinde |  | Pass
Validate the Asset Transfer Page Elements
NA | NA | NA | Not Present | Not Present | Akash Dhole | NA | AMS_64 | AMS_TC_64 | Verify that, Asset Transfer is clickable or not | 1. User should be Login to AMS Application 2. User should be on Asset Transfer page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset Transfer | User should be able to click on "Asset Transfer" link. |  | Nikhil Palde | 2023-02-13 |  |  | Nikhil Palde |  | Pass
|  |  | Not Present | Not Present |  | NA | AMS_65 | AMS_TC_65 | Validate that, UI components/Design of Asset Transfer page | 1. User should be Login to AMS Application 2. User should be on Asset Transfer page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset Transfer 5. Validate "NCS Logo" should be present 6. Verify "Dashboard, Master, Utility, Audit" Options should be present 7. Verify "List of Asset Transfer" Header message should be present 8. Verify "Search Texbox, Search dropdown, Search Button" should be present 9.Verify "List of Asset Transfer" Table should be Present 10. Verify "Items per page" Dropdown should be present | 1. "NCS Logo" should be present 2. "Dashboard, Master, Utility, Audit" Options should be present 3. "List of Asset Trasfer" Header message should be present 4. "Search Texbox, Search dropdown, Search Button" should be present 5."List of Asset Transfer" Table should be Present 6. "Items per page" Dropdown should be present |  | Nikhil Palde | 2023-02-13 |  |  | Nikhil Palde |  | Pass
|  |  | Not Present | Not Present | Akash Dhole | NA | AMS_66 | AMS_TC_66 | Verify that, Search textbox is editable or not | 1. User should be Login to AMS Application 2. User should be on Asset Transfer page | Enter : Nikhil | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset Transfer 5. Click on Serch textbox | User should be able to enter the data and get the records for the same |  | Nikhil Palde | 2023-02-06 |  |  | Nikhil Palde |  | Pass
|  |  | Not Present | Not Present | Akash Dhole | NA | AMS_67 | AMS_TC_67 | Verify that, Search Dropdown is clickable or not | 1. User should be Login to AMS Application 2. User should be on Asset Transfer page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset Transfer 5. Click on Serch Dropdown | User should be able to select the Categories from the dropdown |  | Nikhil Palde | 2023-02-06 |  |  | Nikhil Palde |  | Pass
|  |  | Not Present | Not Present | Akash Dhole | NA | AMS_68 | AMS_TC_68 | Verify that, Search Button is Clickable | 1. User should be Login to AMS Application 2. User should be on Asset Transfer page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset Transfer 5. Select from Search Dropdown 6. Click on Search Button | User should be able to Click on Search Button and Display the Filtered Data |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
|  |  | Not Present | Not Present | Akash Dhole | NA | AMS_69 | AMS_TC_69 | Validate that, UI components/Design of Asset Transfer Table | 1. User should be Login to AMS Application 2. User should be on Asset Transfer page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset Transfer 5. Verify "Asset No, From Department, To Department, Status, Transfer Dtae, Employee Code, Employee Name, Remark, Action"Column Header should be present of Asset Table 6.Verify "Edit, Delete" Button should be present in Action Coloumn | 1. "Asset No, From Department, To Department, Status, Transfer Dtae, Employee Code, Employee Name, Remark, Action"Column Header should be present of Asset Table 2. "Edit, Delete" Button should be present in Action Coloumn |  | Nikhil Palde | 2023-02-01 |  |  | Nikhil Palde |  | Pass
|  |  | Not Present | Not Present | Akash Dhole | NA | AMS_70 | AMS_TC_70 | Verify the "Items per page"dropdown has 3 values | 1. User should be Login to AMS Application 2. User should be on Asset Transfer page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset Transfer 5. Verify "Items per page" Dropdown | 1. "Asset No, From Department, To Department, Status, Transfer Dtae, Employee Code, Employee Name, Remark, Action"Column Header should be present of Asset Table 2. "Edit, Delete" Button should be present in Action Coloumn |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
Validate the Asset Group Page Elements
AMS_MD_7 | AssetsGroupModuleTest | CreateAssetsGroupTest | Completed | Pass | Akash Dhole | NA | AMS_71 | AMS_TC_71 | Verify that, Asset Group is clickable or not | 1. User should be Login to AMS Application 2. User should be on Asset Group page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset Group | User should be able to click on "Asset Transfer" link. |  | Nikhil Palde | 2023-02-13 |  |  | Nikhil Palde |  | Pass
|  | CreateAssetsGroupTest SearchAssetsGroupTest | Completed | Pass | Akash Dhole | Elements that are not automatable: 1. NCS Logo Elements that are not present: 1. Audit option | AMS_72 | AMS_TC_72 | Validate that, UI components/Design of Asset Group page | 1. User should be Login to AMS Application 2. User should be on Asset Group page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset Group 5. Validate "NCS Logo" should be present 6. Verify "Dashboard, Master, Utility, Audit" Options should be present 7. Verify "List of Asset Group" Header message should be present 8. Verify "Search Texbox" should be present 9.Verify "List of Asset Group" Table should be Present 10. Verify "Items per page" Dropdown should be present | 1. "NCS Logo" should be present 2. "Dashboard, Master, Utility, Audit" Options should be present 3. "List of Asset Group" Header message should be present 4. "Search Texbox" should be present 5."List of Asset Group" Table should be Present 6. "Items per page" Dropdown should be present |  | Nikhil Palde | 2023-02-13 |  |  | Nikhil Palde |  | Pass
|  | SearchAssetsGroupTest | Completed | Pass | Akash Dhole | NA | AMS_73 | AMS_TC_73 | Verify that, Search textbox is editable or not | 1. User should be Login to AMS Application 2. User should be on Asset Group page | Enter : Nikhil | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset Group 5. Click on Search textbox | User should be able to enter the data and get the records for the same |  | Nikhil Palde | 2023-02-06 |  |  | Nikhil Palde |  | Pass
|  | CreateAssetsGroupTest | Completed | Pass | Akash Dhole | NA | AMS_74 | AMS_TC_74 | Verify that, Create Asset Group Button is Clickable | 1. User should be Login to AMS Application 2. User should be on Asset Group page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset Group 5. Click on Create New Asset Group | User should be able to Click on Create New Asset Group Button and navigate to new asset group page |  | Nikhil Palde | 2023-02-07 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_75 | AMS_TC_75 | Validate that, UI components/Design of Add Asset Group page | 1. User should be Login to AMS Application 2. User should be on Asset Group page |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset Group 5. Click on Create Asset Group 6. Verify "Create Asset Group" Header message should be present 7.Verify "Asset Group Name" Label with a textbox should be present 8.Verify "Submit" button should be present 9.Verify "Cancel" button should be present | 1. "Create Asset Group" Header message should be present 2. "Asset Group Name" Label with a textbox should be present 3."Submit" button should be present 4."Cancel" button should be present |  | Nikhil Palde | 2023-02-13 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_76 | AMS_TC_76 | Verify that, "Asset Group Name" textbox is editable or not | 1. User should be Login to AMS Application 2. User should be on Asset Group page | Enter : Nikhil | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset Group 5. Click on Add Asset Group 6. Click on Search textbox | User should be able to enter the name for the new asset group |  | Nikhil Palde | 2023-02-06 |  |  | Nikhil Palde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_77 | AMS_TC_77 | Verify that, "Submit" is clickable or not | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset Group 5. Click on Add Asset Group 6. Click on Submit button | User should be to create new asset grooup |  | Nikhil Palde | 2023-02-08 |  |  | Aradhana Shinde |  | Pass
|  |  | Completed | Pass | Akash Dhole | NA | AMS_78 | AMS_TC_78 | Verify that, "Cancel" is clickable or not | 1. User should be on AMS Application |  | 1. Navigate to AMS Application 2. Login to the Application 3. Click on Master 4. Click on Asset Group 5. Click on Add Asset Group 6. Click on Cancel button | User should be navigated back to Asset Group Page |  | Nikhil Palde | 2023-02-08 |  |  | Aradhana Shinde |  | Pass

## User
Module_ID | Automation_Test_Suites | Automation_Test_Cases | Automation Progress | Automation test Status | Automated By | Reamrk | Test case S/N | Test case ID | Test Case Description | Pre-condition | Test Data | Test Steps | Expected Results | Actual Results | Written By | Written On | Last Update Date | Review Comments | Tested By | Reviewed by | Status | Date Tested
AMS_MD_3 | DashboardModuleTest | CreateUserTest | Completed | Pass | Akash | NA | AMS_001 | AMS_Users_01 | The "Users" page link should be clickable | Login to AMS using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Click on "Users"link | The link should be clickable and should navigate user to "Users" page | The link is clickable and navigates user to "Users" page | Aradhana | 23/02/2023 |  |  | Aradhana |  | Close | 23/02/2023
AMS_MD_12 | UserModuleTest | DashboardMasterTest GetAllRowsPresent CreateUserTest | Completed | Pass | Akash | NA | AMS_002 | AMS_Users_02 | The Asset Status page should have following elements present on Users: 1.Page header as "Users". 2.Navigation link. 3.Label "Item per page" 4.Dropwdown box for "Items per page" 6. Textbox for "Search" label. 7. Cross button in the Textbox for the "Search" label 8. "Create Users" button. 9. A table with column names "Employee ID", "Username", "Role", "Email,"Status", and "Actions". 10. Two actions should be displayed in "Actions" column | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "User" sub menu | The Asset Status page should have following elements present on "Users " 1.Page header as "Users". 2.Navigation link. 3.Label "Item per page" 4.Dropwdown box for "Items per page" . 6.Textbox for "Search" label. 7.Cross button in the Textbox for "Search" label 8.Create "Users" button. 9.A table with column name "Employee ID" ,"Username", "Role","Email ,"Status", "Actions". 10.Two actions ashould be dislplayed in "Actions"column | The Asset Status page have following elements present on "Users " 1.Page header as "Users". 2.Navigation link. 3.Label "Item per page" 4.Dropwdown box for "Items per page" . 6.Textbox for "Search" label. 7.Cross button in the Textbox for "Search" label 8.Create "Users" button. 9.A table with column name "Employee ID" ,"Username", "Role","Email ,"Status", "Actions". 10.Two actions ais be dislplayed in "Actions"column | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
NA | NA | NA | Not In Scope | NA | Akash | Element is not automatable. | AMS_003 | AMS_Users_03 | The navigaion link should be clickable | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Users" sub menu 8.Click on "Home/Users" navigation link | The"Home/Users" navigation link should be clickable | The"Home/Users" navigation link is clickable | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
AMS_MD_12 | UserModuleTest | SearchUserTest | Completed | Pass | Akash | NA | AMS_004 | AMS_Users_04 | Verify and validate the "Items per page" dropdown box should have 4 dropdown values and the button is clickable | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Users" sub menu 8.Click on "Items per page" dropdown button | The dropdown button should be clickable and the dropdown should have 4 values 1) 15 2) 25 3) 35 4) 50 | The dropdown button is clickable and the dropdown have 4 values 1) 15 2) 25 3) 35 4) 51 | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  |  | Completed | Pass | Akash | NA | AMS_005 | AMS_Users_05 | Verify and validate the "Search By" textbox have placeholder. | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Users" sub menu | The "Search By " textbox should have "Employee name, id, role etc." placeholder. | The "Search By " textbox have "Employee name, id, role etc." placeholder. | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  | CreateUserTest | Completed | Pass | Akash | NA | AMS_006 | AMS_Users_06 | Verify and validate the "Create User" button is active and displays an pop when clicked | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Users" sub menu 8.Click on "Create User" button | The "Create user" button should be active and should display an pop when clicked | The "Create user" button is active and displays an pop when clicked | Aradhana | 20/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  |  | Completed | Pass | Akash | NA | AMS_007 | AMS_Users_07 | "Create Users "pop should have an following elements present 1.Header "Create User" 2.Label as "User name" 3.Label "User name" should have an text box. 4.Label as "Employee ID " 5.Label "Employee ID" should have an text box 6.Label as "User Email " 7.Label "User Email" should have an text box 8.Label as "Role Name " 9.Label "Role Name" should have an dropdown box with two dropdown values 10.Label as "Password" 11.Label "Password" should have an textbox. 12."Cancel" button 13."Create" button. | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Users" sub menu 8.Click on "Create User" button | "Create Users "pop should have an following elements present 1.Header "Create User" 2.Label as "User name" 3.Label "User name" should have an text box. 4.Label as "Employee ID " 5.Label "Employee ID" should have an text box 6.Label as "User Email " 7.Label "User Email" should have an text box 8.Label as "Role Name " 9.Label "Role Name" should have an dropdown box with two dropdown values 10.Label as "Password" 11.Label "Password" should have an textbox. 12."Cancel" button 13."Create" button. | "Create Users "pop have following elements present 1.Header "Create User" 2.Label as "User name" 3.Label "User name" is have an text box. 4.Label as "Employee ID " 5.Label "Employee ID" is have an text box 6.Label as "User Email " 7.Label "User Email" is have an text box 8.Label as "Role Name " 9.Label "Role Name" is have an dropdown box with two dropdown values 10.Label as "Password" 11.Label "Password" is have an textbox. 12."Cancel" button 13."Create" button. | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  |  | Completed | Pass | Akash | NA | AMS_008 | AMS_Users_08 | "User Name" label textbox should be editable | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Users" sub menu 8.Click on "CreateUser" button 9.Click on"User Name" label textbox | The "User Name" label textbox should be editable | The "User Name" label textbox is editable | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  |  | Completed | Pass | Akash | NA | AMS_009 | AMS_Users_09 | "User ID" label textbox should be editable | Login using admin username | Username:PiysuhChoraria Password: Ncs@124 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Users" sub menu 8.Click on "CreateUser" button 9.Click on"User ID" label textbox | The "User ID" label textbox should be editable | The "User ID" label textbox is editable | Aradhana
|  |  | Completed | Pass | Akash | NA | AMS_010 | AMS_Users_10 | "Role" label dropwdown should be active | Login using admin username | Username:PiysuhChoraria Password: Ncs@125 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Users" sub menu 8.Click on "CreateUser" button 9.Click on"Role" label textbox | The "Role" label dropdown should be active | The "Role" label dropdown is active | Aradhana
|  |  | Completed | Pass | Akash | NA | AMS_011 | AMS_Users_11 | "Password" label textbox should be editable | Login using admin username | Username:PiysuhChoraria Password: Ncs@126 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Users" sub menu 8.Click on "CreateUser" button 9.Click on"Password" label textbox | The "Password" label textbox should be editable | The "Password" label textbox is editable
|  |  | Completed | Pass | Akash | NA | AMS_012 | AMS_Users_12 | "Email" label textbox should be editable | Login using admin username | Username:PiysuhChoraria Password: Ncs@127 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Users" sub menu 8.Click on "CreateUser" button 9.Click on"Email" label textbox | The "Email" label textbox should be editable | The "Email" label textbox is editable
|  |  | Completed | Pass | Akash | NA | AMS_013 | AMS_Users_13 | "Cancel" button should be active and data should remain unaltered | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "User" sub menu 8.Click on "Create User" button 9.Click cancel button | "Cancel" button should be active and when clicked on it previous data should remain unaltered | The "Cancel" button is active and when clicked, create action will be cancelled and popup will be closed. | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  |  | Completed | Pass | Akash | NA | AMS_014 | AMS_Users_14 | "Create button should be active and data should be altered | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "User" sub menu 8.Click on "Create User" button 9.Click "Create" button | "Create button should be active when clicked on it it should alter the previous data with the new data should get updated in the "User" table | The "Create" button is active when clicked, the new data is entered in the "User" data table. | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  |  | Completed | Fail | Akash | The "Record Created Successfully!" message not displaying inside the pop-up. | AMS_015 | AMS_Users_15 | Success message should be displayed as, "Record Created Successfully!" | Login using admin username | Username:PiysuhChoraria Password: Ncs@124 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "User" sub menu 8.Click on "Create User" button 9.Click "Create" button | Success message should be displayed as, "Record Created Successfully!" | The success message is not displayed as, "Record Created Successfully!" | Akash | 2023-04-05 |  |  | Akash |  | NA | 2023-04-05
|  | UpdateUserTest | Completed | Pass | Akash | NA | AMS_016 | AMS_Users_16 | Verify and validate the "Edit User" button is active and displays an pop when clicked | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Users" sub menu 8.Click on "Edit User" button | The "Edit user" button should be active and should display an pop when clicked | The "Edit user" button is active and displays an pop when clicked | Aradhana | 20/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  |  | Completed | Pass | Akash | NA | AMS_017 | AMS_Users_17 | "Edit Users "pop should have an following elements present 1.Header "Create User" 2.Label as "User name" 3.Label "User name" should have an text box. 4.Label as "Employee ID " 5.Label "Employee ID" should have an text box 6.Label as "User Email " 7.Label "User Email" should have an text box 8.Label as "Role Name " 9.Label "Role Name" should have an dropdown box with two dropdown values 10.Label as "Password" 11.Label "Password" should have an textbox. 12."Cancel" button 13."Create" button. | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Users" sub menu 8.Click on "Edit User" button | "Edit Users "pop should have an following elements present 1.Header "Create User" 2.Label as "User name" 3.Label "User name" should have an text box. 4.Label as "Employee ID " 5.Label "Employee ID" should have an text box 6.Label as "User Email " 7.Label "User Email" should have an text box 8.Label as "Role Name " 9.Label "Role Name" should have an dropdown box with two dropdown values 10.Label as "Password" 11.Label "Password" should have an textbox. 12."Cancel" button 13."Create" button. | "Edit Users "pop have following elements present 1.Header "Create User" 2.Label as "User name" 3.Label "User name" is have an text box. 4.Label as "Employee ID " 5.Label "Employee ID" is have an text box 6.Label as "User Email " 7.Label "User Email" is have an text box 8.Label as "Role Name " 9.Label "Role Name" is have an dropdown box with two dropdown values 10.Label as "Password" 11.Label "Password" is have an textbox. 12."Cancel" button 13."Create" button. | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  |  | Completed | Pass | Akash | NA | AMS_018 | AMS_Users_18 | "User Name" label textbox should be editable | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Users" sub menu 8.Click on "Edit User" button 9.Click on"User Name" label textbox | The "User Name" label textbox should be editable | The "User Name" label textbox is editable | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  |  | Completed | Pass | Akash | NA | AMS_019 | AMS_Users_19 | "User ID" label textbox should be editable | Login using admin username | Username:PiysuhChoraria Password: Ncs@124 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Users" sub menu 8.Click on "Edit User" button 9.Click on"User ID" label textbox | The "User ID" label textbox should be editable | The "User ID" label textbox is editable | Aradhana
|  |  | Completed | Pass | Akash | NA | AMS_020 | AMS_Users_20 | "Role" label dropwdown should be active | Login using admin username | Username:PiysuhChoraria Password: Ncs@125 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Users" sub menu 8.Click on "Edit User" button 9.Click on"Role" label textbox | The "Role" label dropdown should be active | The "Role" label dropdown is active | Aradhana
|  |  | Completed | Pass | Akash | NA | AMS_021 | AMS_Users_21 | "Password" label textbox should be editable | Login using admin username | Username:PiysuhChoraria Password: Ncs@126 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Users" sub menu 8.Click on " Edit User" button 9.Click on"Password" label textbox | The "Password" label textbox should be editable | The "Password" label textbox is editable
|  |  | Completed | Pass | Akash | NA | AMS_022 | AMS_Users_22 | "Email" label textbox should be editable | Login using admin username | Username:PiysuhChoraria Password: Ncs@127 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Users" sub menu 8.Click on "Edit User" button 9.Click on"Email" label textbox | The "Email" label textbox should be editable | The "Email" label textbox is editable
|  |  | Completed | Pass | Akash | NA | AMS_023 | AMS_Users_23 | "Cancel" button should be active and data should remain unaltered | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "User" sub menu 8.Click on "Edit User" button 9.Click cancel button | "Cancel" button should be active and when clicked on it previous data should remain unaltered | "Cancel" button is active and when clicked on it previous data remains unaltered | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  |  | Completed | Fail | Akash | "Update" button is not working | AMS_024 | AMS_Users_24 | "Update" button should be active and data should be altered | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "User" sub menu 8.Click on "Edit User" button 9.Click "Create" button | "Create button should be active when clicked on it it should alter the previous data with the new data should get updated in the "User" table | The "Create" button is active when clicked on it alters the previous data with the new data entered in the "User" data table. | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  |  | Completed | Fail | Akash | The "Record Updated Successfully!" message not displaying inside the pop-up. | AMS_025 | AMS_Users_25 | Success message should be displayed as, "Record Updated Successfully!" | Login using admin username | Username:PiysuhChoraria Password: Ncs@124 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "User" sub menu 8.Click on "Create User" button 9.Click "Create" button | Success message should be displayed as, "Record Updated Successfully!" | The success message is not displayed as, "Record Updated Successfully!" | Akash | 2023-04-05 |  |  | Akash |  | NA | 2023-04-05

## AssetStatus
Module_ID | Automation_Test_Suites | Automation_Test_Cases | Automation Progress | Automation test Status | Automated By | Reamrk | Test case S/N | Test case ID | Test Case Description | Pre-condition | Test Data | Test Steps | Expected Results | Actual Results | Written By | Written On | Last Update Date | Review Comments | Tested By | Reviewed by | Status | Date Tested
AMS_MD_3 | DashboardModuleTest | CreateAssetsStatusTest | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_01 | The "Asset Status" page link should be clickable | Login to AMS using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Click on "Asset Status"link | The link should be clickable and should navigate user to "Asset Status" page | The link is clickable and navigates user to "Asset Status" page | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
AMS_MD_10 | AssetsStatusModuleTest | CreateAssetsStatusTest SearchAssetsStatusTest UpdateAssetsStatusTest DeleteAssetsStatusTest | Completed | Pass | Akash Dhole | Elements that are not automatable: 1. Navigation Link Elements that are not present: | AMS_ | AMS_AS_02 | The Asset Status page should have following elements present on "Asset Status " 1.Page header as "Asset Status". 2.Navigation link. 3.Label "Item per page" 4.Dropwdown box for "Items per page" . 6.Textbox for "Search" label. 7.Cross button in the Textbox for "Search" label 8.Create "Asset Status" button. 9.A table with column name "Asset Status ID", Asset Status Name, "Actions". 10.Two actions ashould be dislplayed in "Actions"column | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu | The Asset Status page should have following elements present on "Asset Status " 1.Page header as "Asset Status". 2.Navigation link. 3.Label "Item per page" 4.Dropwdown box for "Items per page" . 6.Textbox for "Search" label. 7.Cross button in the Textbox for "Search" label 8.Create "Asset Status" button. 9.A table with column name "Asset Status ID", Asset Status Name, "Actions". 10.Two actions ashould be dislplayed in "Actions"column | The Asset Status page have following elements present on "Asset Status " 1.Page header as "Asset Status". 2.Navigation link. 3.Label "Item per page" 4.Dropwdown box for "Items per page" . 6.Textbox for "Search" label. 7.Cross button in the Textbox for "Search" label 8.Create "Asset Status" button. 9.A table with column name "Asset Status ID", Asset Status Name, "Actions". 10.Two actions ashould be dislplayed in "Actions"column | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  | NA | Not In Scope | NA | Akash Dhole | Link is not automatable |  | AMS_AS_03 | The navigaion link should be clickable | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu 8.Click on "Home/Status" navigation link | The"Home/Status" navigation link should be clickable | The"Home/Status" navigation link is clickable | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  | SearchAssetsStatusTest | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_04 | Verify and validate the "Items per page" dropdown box should have 4 dropdown values and the button is clickable | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu 8.Click on "Items per page" dropdown button | The dropdown button should be clickable and the dropdown should have 4 values 1) 15 2) 25 3) 35 4) 50 | The dropdown button is clickable and the dropdown have 4 values 1) 15 2) 25 3) 35 4) 51 | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  |  | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_05 | Verify and validate the "Search By" textbox have placeholder. | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu | The "Search By " textbox should have "Employee name, id, role etc." placeholder. | The "Search By " textbox have "Employee name, id, role etc." placeholder. | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  | CreateAssetsStatusTest | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_06 | Verify and validate the "Create Asset Status" button is active and displays an pop when clicked | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu 8.Click on "Create Asset Status" button | The "Create Asset Status" button should be active and should display an pop when clicked | The "Create Asset Status" button is active and displays an pop when clicked | Aradhana | 20/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  |  | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_07 | "Create Asset Status "pop should have an following elements present 1.Header "Create Asset Status" 2.Label as "Asset Status name" 3.Label "Asset Status name" should have an text box. 4.Text box should have "Enter Asset Group Name" as place holder. 5."Cancel" button 6."Create" button. | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu 8.Click on "Create Asset Status" button | "Create Asset Status "pop should have an following elements present 1.Header "Create Asset Status" 2.Label as "Asset Status name" 3.Label "Asset Status name" should have an text box. 4.Text box should have "Enter Asset Group Name" as place holder. 5."Cancel" button 6."Create" button. | "Create Asset Status "pop have following elements present 1.Header "Create Asset Status" 2.Label as "Asset Status name" 3.Label "Asset Status name" have an text box. 4.Text box have "Enter Asset Group Name" as place holder. 5."Cancel" button 6."Create" button. | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  |  | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_08 | "Asset Status Name" label textbox should be editable | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu 8.Click on "Create Asset Status" button 9.Click on"Asset Status Name" label textbox | The "Asset Status Name" label textbox should be editable | The "Asset Status Name" label textbox is editable | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  |  | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_09 | "Asset Status Name" label text box should have focus indicator | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu 8.Click on "Create Asset Status" button 9.Click on"Asset Status Name" label textbox | The "Asset Status Name" label textbox should have focus indicator by highlighting the outline of textbox in blue while editing | The "Asset Status Name" label textbox have focus indicator which highlights the outline of textbox in blue while editing | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  |  | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_10 | "Cancel" button should be active and data should remain unaltered | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu 8.Click on "Create Asset Status" button 9.Click cancel button | "Cancel" button should be active and when clicked on it previous data should remain unaltered | "Cancel" button should is active and when clicked on it previous data remains unaltered | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  |  | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_11 | "Create button should be active and data should be altered | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu 8.Click on "Create Asset Status" button 9.Click "Create" button | "Create button should be active when clicked on it it hsould alter the previous data with the new data entered in the "Asset Status Name" textbox | "Create button is active when clicked onit it alter the previous data with the new data entered in the "Asset Status Name" textbox | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  | SearchAssetsStatusTest | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_12 | The "Search By" label textbox should filter the results according to the "Asset Status" entered | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 Search By Textbox : "Pending" | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu 8.Click on "Create Asset Status" button 9.Ener data in "Search By" textbox | The "Search By" textbox should filter the data according to the data entered in textbox | The "Search By" textbox filters the data according to the data entered in textbox | Aradhana | 22/02/2023 |  |  | Aradhana |  | Close | 22/02/2023
|  | UpdateAssetsStatusTest DeleteAssetsStatusTest | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_13 | The "Actions"column should have two actions 1. Delete 2. Edit | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu 8.Click on "Create Asset Status" button 9.Ener data in "Search By" textbox | The "Actions" column should have two action buttons 1.Delete 2. Edit | The "Actions" column have two action buttons 1.Delete 2.Edit | Aradhana |  |  |  | Aradhana
|  | DeleteAssetsStatusTest | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_14 | The "Delete"action button should have tooltip | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu 8.Hover on Delete button | The "Delete"action button should have tooltip when hover over it | The "Delete"action button have tooltip when hovered over it | Aradhana |  |  |  | Aradhana
|  | UpdateAssetsStatusTest | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_15 | The "Edit"action button should have tooltip | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu 8.Hover on "Edit" button. | The "Edit"action button should have tooltip when hover over it | The "Edit"action button have tooltip when hovered over it | Aradhana |  |  |  | Aradhana
|  | DeleteAssetsStatusTest | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_16 | Verify and validate that the "Delete" pop arrives when clicked on "Delete" button | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu 8.Click on "Delete" button. | The "Delete" pop should arrive when clicked on "Delete" button | The "Delete" pop arrive when clicked on "Delete" button | Aradhana |  |  |  | Aradhana
|  |  | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_17 | Verify and validate that the "Delete" pop arrives when clicked on "Delete" button | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu 8.Click on "Edit" action button. | The "Edit Status" pop should arrive when clicked on "Edit" button | The "Edit Status" pop arrives when clicked on "Edit" button | Aradhana |  |  |  | Aradhana
|  | UpdateAssetsStatusTest | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_18 | Verify and validate "Edit Status" pop should have following element present 1."Edit Status" header. 2."Status Name" label 3. Textbox for label "Status Name". 4."Enter Name" placeholder for "Status Name" label textbox. 5."Cancel" button. 6."update" button. | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu 8.Click on "Edit" action button. | Following elements should be present on Edit Status pop up 1."Edit Status" header. 2."Status Name" label 3. Textbox for label "Status Name". 4."Enter Name" placeholder for "Status Name" label textbox. 5."Cancel" button. 6."Save" button. | Following elements are present on "Edit Status" popup 1."Edit Status" header. 2."Status Name" label 3. Textbox for label "Status Name". 4."Enter Name" placeholder for "Status Name" label textbox. 5."Cancel" button. 6."Save" button. | Aradhana |  |  |  | Aradhana
|  |  | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_19 | Verfiy and validate the " Asset Group Name" label textbox is editable and have focus indicator | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 Asset Group Name (textbox) : Allocated | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu 8.Click on "Edit" action button. 9.Edit the "Asset Group Name" label textbox | The textbox should be editable and should have focus indicator | The textbox is editable and have focus indicator
|  |  | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_20 | Verify and validate the "Cancel" button closes and form and refreses the pop if any previous data present in fields | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 Asset Group Name (textbox) : Allocated | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu 8.Click on "Edit" action button. 9.Edit the "Asset Group Name" label textbox | The "Cancel" button should close the pop up and delete any previous data present in textbox | The "Cancel" button closes the pop up and delete any previous data present in textbox
|  |  | Completed | Pass | Akash Dhole | NA | AMS_ | AMS_AS_21 | Verify and validate that the "Update" button changes the status of resptective asset. | Login using admin username | Username:PiysuhChoraria Password: Ncs@123 Asset Group Name (textbox) : Allocated | 1.Navigate to AMS Login Page. 2.Enter username. 3.Enter Password. 4.Click on Submit. 5.Click on cancel button for update user popup. 6.Click on "Master" in sidebar menu. 7.Click on "Asset Status" sub menu 8.Click on "Edit" action button. 9.Edit the "Asset Group Name" label textbox | The update button should change the status of respective asset | The update button changes the status of respective asset

## Audit
Test case S/N | Test case ID | Test Case Description | Pre-condition | Test Data | Test Steps | Expected Results | Actual Results | Written By | Written On | Last Update Date | Review Comments | Tested By | Reviewed by | Status | Date Tested
AMS_01 | AMS_AU_01 | Verify "Audit" link should be clickable | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link | User should be able to click on "Audit" link | User is able to click on "Audit" link | Aradhana |  |  |  | Aradhana |  | Close
AMS_02 | AMS_AU_02 | Verify "Audit"link has following list items 1.Asset Audit 2.Asset Transfer Audit. 3.Employee Audit 4.Asset Group Audit. 5.Asset Department Audit. 6.Asset Vendor Audit 7.Asset Status Audit 8.Users Audit 9.Login Tracker | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link | User should be able to view the list items | User is able to view the list items | Aradhana |  |  |  | Aradhana |  | Close
AMS_03 | AMS_AU_03 | Verify "Asset Transfer Audit" link is clickable | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Asset Audit" link | User should be able to click on "Asset Tranfer Audit"link. | "Asset Transfer Audit" link is clickable | Aradhana |  |  |  | Aradhana |  | Close
AMS_04 | AMS_AU_04 | Verfiy "Employee Audit" link is clickable | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Employee Audit". | User should be able to click on "Employee Audit"link. | "Employee Audit" link is clickable | Aradhana |  |  |  | Aradhana |  | Close
AMS_05 | AMS_AU_05 | Verfiy "Asset Group Audit" link is clickable | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Asset Group Audit". | User should be able to click on "Asset Group Audit"link. | "Asset Group Audit" link is clickable | Aradhana |  |  |  | Aradhana |  | Close
AMS_06 | AMS_AU_06 | Verfiy "Asset Department Audit" link is clickable | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Asset Department Audit". | User should be able to click on "Asset Department Audit"link. | "Asset Department Audit" link is clickable | Aradhana |  |  |  | Aradhana |  | Close
AMS_07 | AMS_AU_07 | Verfiy "Asset Vendor Audit" link is clickable | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Asset Vendor Audit". | User should be able to click on "Asset Vendor Audit"link. | "Asset Vendor Audit" link is clickable | Aradhana |  |  |  | Aradhana |  | Close
AMS_08 | AMS_AU_08 | Verfiy "Asset Status Audit" link is clickable | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Asset Status Audit". | User should be able to click on "Asset Status Audit"link. | "Asset Status Audit" link is clickable | Aradhana |  |  |  | Aradhana |  | Close
AMS_09 | AMS_AU_09 | Verfiy "Users Audit" link is clickable | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Users Audit". | User should be able to click on "Users Audit"link. | "Users Audit" link is clickable | Aradhana |  |  |  | Aradhana |  | Close
AMS_10 | AMS_AU_10 | Verfiy "Login Tracker" link is clickable | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Login Tracker". | User should be able to click on "Login Tracker"link. | "Login Tracker" link is clickable | Aradhana |  |  |  | Aradhana |  | Close
Asset Audit
AMS_11 | AMS_AU_11 | Verify "Asset Audit" page header | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. 3.Click on "Audit" link |  | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Asset Audit". | User should be able to view the page hearder as "List of Asset Audit". | "List of Asset Audit " is present on "Asset Audit " page | Aradhana |  |  |  | Aradhana |  | Close
AMS_12 | AMS_AU_12 | Verify the "Export Assets" button is present and is clickable | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. 3.Click on "Audit" link | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Asset Audit". 8.Click on "Export Assets" button. | User should be able to view and click on the "Export Asset" button | "Export Assets" button is present and clickable | Aradhana |  |  |  | Aradhana |  | Close
AMS_13 | AMS_AU_13 | Verify "Search" textbox is present and editable | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. 3.Click on "Audit" link | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Asset Audit". 8.Click on "Search" textbox. | User should be able to view and edit the "Search" textbox | "Search" textbox is visible and editable | Aradhana |  |  |  | Aradhana |  | Close
AMS_14 | AMS_AU_14 | Verfiy when clicked on "Export Assets" button it downloads an excel file | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. 3.Click on "Audit" link | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Asset Audit". 8.Click on "Export Assets" textbox. | User should be able to download excel file | Excel file gets downloaded | Aradhana |  |  |  | Aradhana |  | Close
AMS_15 | AMS_AU_15 | Verify the "Asset Audit" page have table data present. | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Asset Audit". | User should be able to view the table on "Asset Audit " page. | Table is present | Aradhana |  |  |  | Aradhana |  | Close
AMS_16 | AMS_AU_16 | Verify the columns of the table | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Asset Audit". | The table should consist of following column names. 1.Version 2.Action. 3.Asset ID. 4.Asset No. 5.Asset Serial No. 6.Description 7.Category 8.Asset Group. 9.Enviroment 10.Department 11.Vendor 12.Employee Code. 13.Employee Nmae. 14.Status 15.Reason 16. Last Modify 17.Created By 18.Captialisation Date. | Table consist of all the required column names 1.Version 2.Action. 3.Asset ID. 4.Asset No. 5.Asset Serial No. 6.Description 7.Category 8.Asset Group. 9.Enviroment 10.Department 11.Vendor 12.Employee Code. 13.Employee Nmae. 14.Status 15.Reason 16. Last Modify 17.Created By 18.Captialisation Date. | Aradhana |  |  |  | Aradhana |  | Close
AMS_17 | AMS_AU_17 | Verify the table displays data | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Asset Audit". | The table should display data | The table does not display data | Aradhana |  |  |  | Aradhana |  | Close
AMS_18 | AMS_AU_18 | Verify "Items per page" label is present | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Asset Audit". | User should be able to view "Items per page" this label. | "Items per page" this label is visible | Aradhana |  |  |  | Aradhana |  | Close
AMS_19 | AMS_AU_19 | Verify there is dropdown for "Items per page" this label | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Asset Audit". | User should be able to click on dropdown and select the item from dropdown list | User is able to click on dropdown and select a list from item. | Aradhana |  |  |  | Aradhana |  | Close
AMS_20 | AMS_AU_20 | Verify the "Items per page"dropdown has 3 values | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Asset Audit". | User should be able to view following 3 list items in the "Items per page"dropdown list 1. 10 2. 20 3. 30 | User is able to view following 3 list items in the "Items per page"drop down list 1. 10 2. 20 3. 30 | Aradhana |  |  |  | Aradhana |  | Close
AMS_21 | AMS_AU_21 | Verify Asset Audit page have pag navigator-icon to direct to first page | 1.Navigate to AMS application 2.Should have the UserID and password for "Admin" role. | 1.roleName: "ADMIN" 2.username: "PiyushChoraria" 3. password: "Ncs@123" | 1.Navigate to AMS application 2.Select Role 3.Enter Userid 4.Enter password 5.Click on "Login" 6.Click on "Audit" link 7.Click on "Asset Audit". | User should be able to view the page navigator icon for navigating to first page | Page navigator icon is

## Sheet1
Test case S/N | Test case ID | Test Case Description | Pre-condition | Test Data | Test Steps | Expected Results | Actual Results | Written By | Written On | Last Update Date
AMS |  | Login | User should be present on Login Page | Username: PiyushChoraria | 1.Navigate to AMS application | The user should be able to Login the application | The user is able to login the apllication | Aradhana
|  |  |  | Password: Ncs@123 | 2.Enter valid username
3.Enter valid password
4.Click on Login button
AMS |  | Verify the user should able to create an asset | The user should have username and password | Username: PiyushChoraria | 1.Navigate to AMS application | The user should be able to create an Asset. | Asset gets created | Aradhana
|  |  |  | Password: Ncs@123 | 2.Enter valid username
|  |  |  | Asset Number: 123321 | 3.Enter valid password
|  |  |  | Asset Serial Number: 545454 | 4.Click on Login button
|  |  |  | Location : IT-07 | 5.Click on Master menu.
|  |  |  | Asset description : Dell | 6.Click on Assets submenu
|  |  |  | Select Asset group:Office Eq(60Mth) | 7.Click on "Create Asset" button
|  |  |  | Select Asset Department: IT | 8.Enter Asset Number
|  |  |  | Select Asset vendor:Om Sai | 9.Enter Asset Serial Number
|  |  |  | Select Asset Type: Movable | 10.Location
|  |  |  | Count : 1 | 11.Asset Description
|  |  |  | Enter Remarks : Allocated | 12.Select Asset Group
13.Select Asset Department
14.Select Vendor
15.Select Asset Type
16.Enter count
17. Enter Remarks
18.Click on Create button
|  | Verify the "Cancel" button closes the "Create asset form" | The user should have username and password | Username: PiyushChoraria | 1.Navigate to AMS application | The create Asset from should be closed | The Create Asset from gets closed | Aradhana
|  |  |  | Password: Ncs@123 | 2.Enter valid username
3.Enter valid password
4.Click on Login button
5.Click on Master menu.
6.Click on Assets submenu
7.Click on "Create Asset" button
8.Click on Cancel button
|  | Verify the user can search paritcular asset | The user should have username and password | Username: PiyushChoraria | 1.Navigate to AMS application | The user should be able to Search particular Asset | The user is able to search particular Asset | Aradhana
|  |  |  | Password: Ncs@123 | 2.Enter valid username
|  |  |  | Search By:123321 | 3.Enter valid password
4.Click on Login button
5.Click on Master menu.
6.Click on Assets submenu
7.Enter Asset number in Search By tetx box
|  | Verify the user can edit the Asset Info | The user should have username and password | Username:PiyushChoraria | 1.Navigate to AMS application
|  |  |  | Password: Ncs@123 | 2.Enter valid username
|  |  |  | Location: IT-03 | 3.Enter valid password
4.Click on Login button
5.Click on Master menu.
6.Click on Assets submenu
7.Enter Asset number in Search By tetx box
8.Click on edit icon fro Actions Icon
|  | Verify the user can delete an particular asset | The user should have username and password | Username: PiyushChoraria | 1.Navigate to AMS application | The Asset should get deleted | The Asset gets deleted | Aradhana
|  |  |  | Password: Ncs@123 | 2.Enter valid username
|  |  |  | Search By : 123321 | 3.Enter valid password
4.Click on Login button
5.Click on Master menu.
6.Click on Assets submenu
7.Enter Asset number in Search By tetx box
8.Click on "Delete" icon in Actions column
Employees
|  | Verify the user can create Employee | The user should have user name and password | Username: PiyushChoraria | 1.Navigate to AMS application | The User should be able to create an Employee | The user can create Employee | Aradhana
|  |  |  | Password: Ncs@123 | 2.Enter valid username
|  |  |  | Employee ID: 1345360 | 3.Enter valid password
|  |  |  | Employee Name : Aradhana | 4.Click on Login button
|  |  |  | Status :Active | 5.Click on Master menu.
|  |  |  | Joining Date: 30/3/2023 | 6.Click on Employees submenu
|  |  |  | Email Id: aradhana@in.ncs-sg.com | 7.Click on "Create Employee" button
8.Enter Employee Id
9. Enter Employee Name
10.Select Status
11. Select Joining Date
12.Enter Email-ID
13.Click on "Save" button
|  | Verify the user can click on close button of create employee form | The user should have user name and password | Username: PiyushChoraria | 1.Navigate to AMS application | The user should be able to click on close button | The user can click on close button | Aradhana
|  |  |  | Password: Ncs@123 | 2.Enter valid username
|  |  |  | Employee ID: 1345360 | 3.Enter valid password
|  |  |  | Employee Name : Aradhana | 4.Click on Login button
|  |  |  | Status :Active | 5.Click on Master menu.
|  |  |  | Joining Date: 30/3/2023 | 6.Click on Employees submenu
|  |  |  | Email Id: aradhana@in.ncs-sg.com | 7.Click on "Create Employee" button
8.Enter Employee Id
9. Enter Employee Name
10.Select Status
11. Select Joining Date
12.Enter Email-ID
13.Click on "Close" button
|  | Verify the user can search the desired employee by entering Employee Name in search by text box | The user should have user name and password | Username: PiyushChoraria | 1.Navigate to AMS application | The user should be able to search the particular employee | The user is able to search particular employee | Aradhana
|  |  |  | Password: Ncs@123 | 2.Enter valid username
|  |  |  | Employee ID: 1345360 | 3.Enter valid password
|  |  |  | Employee Name : Aradhana | 4.Click on Login button
|  |  |  | Status :Active | 5.Click on Master menu.
|  |  |  | Joining Date: 30/3/2023 | 6.Click on Employees submenu
|  |  |  | Email Id: aradhana@in.ncs-sg.com | 7.Click on "Create Employee" button
|  |  |  | Search By : Aradhana | 8.Enter Employee Id
9. Enter Employee Name
10.Select Status
11. Select Joining Date
12.Enter Email-ID
13.Click on "Save" button
14.Enter Employee Name in Search By text box
|  | Verify the user can create Employee , search it and delete that employee | The user should have user name and password | Username: PiyushChoraria | 1.Navigate to AMS application | The user should be able to create an employee, search it and delete it | The can create an employee, search it and delete it | Aradhana
|  |  |  | Password: Ncs@123 | 2.Enter valid username
|  |  |  | Employee ID: 1345360 | 3.Enter valid password
|  |  |  | Employee Name : Aradhana | 4.Click on Login button
|  |  |  | Status :Active | 5.Click on Master menu.
|  |  |  | Joining Date: 30/3/2023 | 6.Click on Employees submenu
|  |  |  | Email Id: aradhana@in.ncs-sg.com | 7.Click on "Create Employee" button
8.Enter Employee Id
9. Enter Employee Name
10.Select Status
11. Select Joining Date
12.Enter Email-ID
13.Click on "Save" button
14.Enter Employee Name in Search By text box
15.Click on delete icon from Actions Column
Request
|  | Verify the User can create Transfer request | The user should have user name and password | Username:PiyushChoraria
Password: Ncs@123
To Location : IT-07
To Employee : Aradhana
Remarks: Please Tranfer the Asset